## Metrics Master List
Category | Metric | What It Measures | How to Collect | Automation Level | Frequency | Target / Benchmark | Why It Matters for ICP Pitch
PRODUCT USAGE METRICS
Product Usage | Total Sessions | Number of times GameMaster AI was launched | App analytics (auto-log each session start) | Fully Automated | Daily auto-log | 50+ sessions / 30 days | Proves demand exists even in low-traffic venue
Product Usage | Unique Users | Distinct groups/individuals who used the product | Unique device ID or session token | Fully Automated | Daily auto-log | 25+ unique users / 30 days | Shows breadth of adoption beyond repeat users
Product Usage | Sessions per Day | Average daily usage rate | Session count / days active | Fully Automated | Daily auto-log | 2+ sessions/day | Demonstrates consistent demand vs one-time curiosity
Product Usage | Peak Usage Hours | When people use GameMaster AI most | Timestamp on each session | Fully Automated | Daily auto-log | Identify top 3 hours | Helps ICP venues schedule staff & plan events around demand
Product Usage | Session Duration (avg) | How long each teaching session lasts | Time from session start to end | Fully Automated | Per session | 10-20 min avg | Proves AI teaches faster than human staff or rulebook reading
Product Usage | Games Taught (by title) | Which specific games are being learned | Log game title per session | Fully Automated | Per session | Track top 10 games | Shows ICP venues which games drive engagement — helps them stock inventory
Product Usage | Repeat Usage Rate | % of users who come back for another game | Compare unique IDs across sessions | Fully Automated | Weekly rollup | 20%+ repeat rate | Proves stickiness — people come back because of the tool
COMPLETION & QUALITY METRICS
Completion | Session Completion Rate | % of sessions where user finishes learning & starts playing | Track 'game started' event after teaching | Fully Automated | Per session | 80%+ completion | THE key stat — proves the product actually works
Completion | Drop-off Point | Where in the teaching flow users quit | Log which step/section user was on at exit | Fully Automated | Per session | Identify top 3 drop-offs | Tells you exactly what to fix in the product
Completion | Questions Asked per Session | How many follow-up questions users ask the AI | Count user inputs per session | Fully Automated | Per session | 3-5 avg is healthy | Low = too simple or not engaging. High = confusing. Sweet spot = interactive
Completion | Error / Fallback Rate | How often the AI can't answer or gives wrong info | Log 'I don't know' or fallback responses | Fully Automated | Per session | <5% fallback rate | Proves reliability — critical for cafe owner trust
Completion | Game Complexity vs Completion | Does completion drop for complex games? | Cross-reference game weight rating with completion | Semi-Automated | Weekly analysis | Maintain 70%+ even for complex games | Shows the product scales across game difficulty
USER SATISFACTION METRICS
Satisfaction | Post-Session Rating | Thumbs up/down or 1-5 stars after each session | In-app prompt after session ends | Fully Automated | Per session | 4.0+ avg / 80%+ thumbs up | Direct social proof for pitch deck and case studies
Satisfaction | Written Feedback | Optional comment box for qualitative feedback | In-app text field after rating | Fully Automated | Per session | Collect 10+ comments | Real customer quotes are marketing gold
Satisfaction | Net Promoter Score (NPS) | Would you recommend this to a friend? (0-10) | In-app survey at session 3+ for repeat users | Fully Automated | After 3rd session | NPS 30+ | Industry-standard metric that ICP owners understand
BUSINESS IMPACT METRICS (requires some manual effort)
Business Impact | Dwell Time Change | Do groups stay longer when using GameMaster AI? | Compare avg visit duration: AI users vs non-users (ask staff) | Manual — staff observation | Weekly estimate | 30+ min longer stays | Directly ties to food/bev revenue argument for ICP pitch
Business Impact | Food & Bev Correlation | Do AI-taught groups buy more? | Track if groups that used AI placed food/bev orders (POS or staff notes) | Manual — POS check | Weekly estimate | Any positive signal | The revenue multiplier proof point ICP owners need to see
Business Impact | Game Purchase Correlation | Do people buy the game after learning it? | Track game sales on days with high AI usage vs low | Manual — POS check | Weekly comparison | Any positive signal | Impulse purchase angle — teaches game → loves it → buys it
Business Impact | Staff Time Freed | Hours staff would have spent teaching that AI handled | Multiply sessions × avg human teach time (est. 20 min) | Semi-Automated | Weekly calc | 10+ hrs/month freed | Directly translates to dollar savings for labor replacement pitch
DISCOVERY & ADOPTION METRICS
Adoption | Self-Discovery Rate | % of users who found and started AI without staff help | Track if session started within 60s of app opening (no staff prompt) | Semi-Automated | Per session | 50%+ self-discovery | Proves product works even without staff promotion — key for non-ICP learning
Adoption | Staff-Prompted vs Organic | How often staff directs customers vs customers find it | Add 'how did you find this?' prompt at session start | Fully Automated | Per session | Track ratio | If organic is high, product sells itself. If staff-prompted is high, need good staff buy-in at ICP
Adoption | Time to First Interaction | How long the device sits before someone uses it | Log time between device activation and first session each day | Fully Automated | Daily | < 2 hours | Visibility/placement insight — helps advise ICP venues on setup
TECHNICAL PERFORMANCE METRICS
Technical | App Load Time | How fast the app launches | Performance monitoring in-app | Fully Automated | Per session | < 3 seconds | Slow load = users walk away. Must be snappy for cafe environment
Technical | Voice Recognition Accuracy | % of voice inputs correctly understood | Compare STT output to intent match rate | Fully Automated | Per session | 90%+ accuracy | Noisy cafe environment is the hardest test — great data
Technical | Crash / Error Rate | How often the app crashes or throws errors | Error logging / crash reporting | Fully Automated | Per session | < 1% crash rate | Reliability metric — can't have crashes during customer experience
Technical | Ambient Noise Performance | Does voice recognition degrade in noisy environments? | Correlate accuracy with time of day / noise levels | Semi-Automated | Weekly analysis | Maintain 85%+ in peak hours | Cafe-specific insight no lab test can give you

## Implementation Sprint
Sprint | Task | Description | Priority | Effort (hrs) | Dependencies | Owner | Status | Due Date
PRE-TRIAL SPRINT — Week Before Trial (3-5 days)
Sprint 0: Pre-Trial | Set up analytics framework | Implement session logging: start time, end time, game title, unique session ID. Use lightweight analytics (Mixpanel free tier, PostHog, or custom Firebase). | P0 — Critical | 4 | None | Tim | Not Started
Sprint 0: Pre-Trial | Build session event tracking | Log key events: session_start, game_selected, teaching_step_completed, session_end, game_started_playing | P0 — Critical | 3 | Analytics framework | Tim | Not Started
Sprint 0: Pre-Trial | Add post-session feedback UI | After session ends: thumbs up/down + optional comment box + optional NPS (0-10). Keep it to ONE screen, 10 seconds max. | P0 — Critical | 3 | None | Tim | Not Started
Sprint 0: Pre-Trial | Implement error/fallback logging | Log every instance where AI returns 'I don't know', gives a fallback response, or user repeats a question | P1 — High | 2 | Analytics framework | Tim | Not Started
Sprint 0: Pre-Trial | Add discovery tracking | Log how session started: 'how did you find this?' quick-tap (saw it on table / staff told me / friend showed me) | P1 — High | 1 | Analytics framework | Tim | Not Started
Sprint 0: Pre-Trial | Voice recognition accuracy logging | Log STT confidence scores per utterance. Flag low-confidence inputs. | P1 — High | 2 | None | Tim | Not Started
Sprint 0: Pre-Trial | Create analytics dashboard | Simple dashboard (Google Sheets auto-import or lightweight web dashboard) to monitor metrics in real-time without visiting venue | P2 — Medium | 4 | Analytics framework | Tim | Not Started
Sprint 0: Pre-Trial | Prepare device & placement plan | Charge device, test app, prepare signage ('Learn any game in minutes — tap to start'). Plan table/counter placement for max visibility. | P0 — Critical | 1 | None | Tim | Not Started
SPRINT 1 — Days 1-7: Launch & Baseline
Sprint 1: Days 1-7 | Deploy to venue | Set up device, brief any available staff (keep to 2 minutes: 'just point people to it if they look confused about a game'). Take photos of placement. | P0 — Critical | 2 | Pre-trial complete | Tim | Not Started
Sprint 1: Days 1-7 | Monitor daily for first 3 days | Check dashboard daily for crashes, errors, zero-session days. Fix critical bugs immediately. | P0 — Critical | 1 | Dashboard built | Tim | Not Started
Sprint 1: Days 1-7 | Establish baseline metrics | After 7 days: document baseline sessions/day, completion rate, avg duration, top games, peak hours | P1 — High | 1 | 7 days of data | Tim | Not Started
Sprint 1: Days 1-7 | Identify top 3 drop-off points | Review session flow data — where are people quitting? Which teaching steps lose people? | P1 — High | 2 | 7 days of data | Tim | Not Started
Sprint 1: Days 1-7 | Collect first feedback batch | Review all thumbs up/down and written comments. Categorize into themes. | P1 — High | 1 | Feedback UI live | Tim | Not Started
SPRINT 2 — Days 8-21: Iterate & Deepen
Sprint 2: Days 8-21 | Fix top 3 product issues | Based on drop-off data and feedback, ship fixes for the biggest friction points | P0 — Critical | 6 | Sprint 1 analysis | Tim | Not Started
Sprint 2: Days 8-21 | Add game complexity tagging | Tag each game with BGG weight rating. Cross-reference with completion rates. | P2 — Medium | 2 | Session data flowing | Tim | Not Started
Sprint 2: Days 8-21 | Manual data collection visit | Visit venue once. Observe for 2-3 hours: Are people finding it? How long do groups stay? Do they order food? Ask staff informally about any changes they've noticed. | P1 — High | 3 | 2+ weeks of data | Tim | Not Started
Sprint 2: Days 8-21 | Voice accuracy analysis | Pull STT confidence logs. Calculate accuracy by time of day. Identify if noisy periods degrade performance. | P1 — High | 2 | Voice logging active | Tim | Not Started
Sprint 2: Days 8-21 | Repeat user analysis | How many unique users came back for a 2nd+ session? What games did they try next? | P1 — High | 1 | 14+ days of data | Tim | Not Started
SPRINT 3 — Days 22-30: Package & Extract
Sprint 3: Days 22-30 | Final metrics snapshot | Pull all 30-day metrics into a summary. Calculate final averages, totals, and trends. | P0 — Critical | 3 | 30 days complete | Tim | Not Started
Sprint 3: Days 22-30 | Build case study one-pager | Create a one-page PDF: venue type, key stats (sessions, completion rate, satisfaction, games taught), top customer quotes, before/after observations | P0 — Critical | 4 | Final metrics | Tim | Not Started
Sprint 3: Days 22-30 | Calculate derived business metrics | Estimate: staff hours saved, potential dwell time increase, implied food/bev revenue lift. Use conservative assumptions. | P1 — High | 2 | Final metrics | Tim | Not Started
Sprint 3: Days 22-30 | Extract top 5 customer quotes | Pull the best written feedback comments. Get permission to use if possible (or anonymize). | P1 — High | 1 | Feedback data | Tim | Not Started
Sprint 3: Days 22-30 | Product improvement roadmap | Based on all 30 days of data: what are the top 5 product improvements before pitching ICP venues? | P1 — High | 2 | All sprint data | Tim | Not Started
Sprint 3: Days 22-30 | Retrieve device & close trial | Pick up device. Thank owner. Don't hard-sell — if they're interested, they'll ask. If not, you already got what you came for. | P0 — Critical | 1 | Day 30 | Tim | Not Started
Sprint 3: Days 22-30 | Update ICP pitch deck with real data | Replace placeholder numbers in your pitch deck with actual trial results. This is the whole point. | P0 — Critical | 3 | Case study done | Tim | Not Started

## 30-Day Tracker
Day | Date | Total Sessions | Unique Users | Avg Duration (min) | Completion Rate % | Avg Rating (1-5) | Top Game | Feedback Comments | Errors/Crashes | Notes | Cumulative Sessions
1 | [10 empty] | 0
2 | [10 empty] | 0
3 | [10 empty] | 0
4 | [10 empty] | 0
5 | [10 empty] | 0
6 | [10 empty] | 0
7 | [10 empty] | 0
8 | [10 empty] | 0
9 | [10 empty] | 0
10 | [10 empty] | 0
11 | [10 empty] | 0
12 | [10 empty] | 0
13 | [10 empty] | 0
14 | [10 empty] | 0
15 | [10 empty] | 0
16 | [10 empty] | 0
17 | [10 empty] | 0
18 | [10 empty] | 0
19 | [10 empty] | 0
20 | [10 empty] | 0
21 | [10 empty] | 0
22 | [10 empty] | 0
23 | [10 empty] | 0
24 | [10 empty] | 0
25 | [10 empty] | 0
26 | [10 empty] | 0
27 | [10 empty] | 0
28 | [10 empty] | 0
29 | [10 empty] | 0
30 | [10 empty] | 0
30-DAY TOTALS |  | 0 | 0 | [5 empty] | 0

## Case Study Template
VENUE INFORMATION
Venue Name
Location
Business Model | Lending library / Café / Hybrid
Cover Charge? | Yes / No — Amount:
Teaching Staff? | Yes / No
CRM / Outreach? | Yes / No
ICP Fit? | Yes / No — Notes:
TRIAL DETAILS
Trial Start Date
Trial End Date
Device Placement
Staff Briefed? | Yes / No
KEY METRICS (30-Day)
Total Sessions
Unique Users
Avg Session Duration
Session Completion Rate
Avg User Rating
Top 3 Games Taught | 1. 2. 3.
Repeat Usage Rate
Error / Crash Rate
Voice Accuracy Rate
BUSINESS IMPACT ESTIMATES
Est. Staff Hours Saved | Total Sessions × 20 min avg human teach time
Est. Dwell Time Increase
Food/Bev Correlation
Game Sales Correlation
TOP CUSTOMER QUOTES
Quote 1
Quote 2
Quote 3
Quote 4
Quote 5
PRODUCT LEARNINGS
Top Drop-off Points | 1. 2. 3.
Games with Lowest Completion
Most Common User Questions
Voice Recognition Issues
Key Product Improvements Needed | 1. 2. 3. 4. 5.
PITCH DECK UPDATES
Stats to Add to Deck
Quotes to Feature
Before/After Story

## Effort Summary
Sprint | Total Tasks | Total Hours | Your Time On-Site | Goal
Sprint 0: Pre-Trial (Week Before) | 8 | 20 | 0 hrs — all remote dev work | Ship analytics + feedback UI. Prep device.
Sprint 1: Days 1-7 | 5 | 7 | 2 hrs — deploy + brief staff | Establish baselines. Fix critical bugs.
Sprint 2: Days 8-21 | 5 | 14 | 3 hrs — one observation visit | Iterate product. Deepen data.
Sprint 3: Days 22-30 | 7 | 16 | 1 hr — retrieve device | Package everything into case study + updated pitch.
TOTAL | 25 | 57 | ~6 hrs on-site over 30 days | Complete trial data + case study + updated pitch deck